## Planning Template
Capital Project - Estimation Worksheet
(Sample entries are provided for illustration purposes only and will need to be updated to reflect actual project financing.)
Project Costs
Cost Distribution
| a | Planning / Construction Costs |  | 250000 | 87.54%
| b | Add Contingency Expense | 10% | 25000 | 8.754%
| c | Add Allowance for Uncollectable Pledges | 10% | 5000 | 1.751%
| d | Add Debt Service Expense |  | 5579 | 1.954%
| e | Total Project Cost |  | 285579 | 100%
Project Funding
% of Project Cost
Cash on Hand
| f | Diocese of Winona Deposit and Loan Fund |  | 235579
| g | Additional Cash Required |  | 0
| h | Sub-Total: Required Cash |  | 235579 | 82.49%
Pledges Receivable
| i | Current Documented Receivables / Pledges |  | 50000
| j | Additional Receivables / Pledges Required |  | 0
| k | Sub-Total: Required Pledges |  | 50000 | 17.51%
| l | Total Project Funding |  | 285579 | 100%
| m | Project Surplus / (Shortfall) |  | 0
Tips for Completing Estimation Worksheet
| 1 | Enter project planning / construction cost in the on line "a".
| 2 | Enter current cash on hand held in the Diocese of Winona Deposit and Loan Fund on line "f".
| 3 | Enter current documented pledges on line "i".
| 4 | Enter allowance percentage for contingency expense; 10.0% of line "a" is recommended.
| 5 | Enter allowance percentage for uncollectable pledges; 10.0% of line "k" is recommended. If project is fully funded by cash on hand, no pledge allowance is required.
| 6 | Enter estimated debit service expense for project loan, (if required); a conservative rate of 7% is recommended. A basic loan amortization calculator is available on bankrate.com (http://tinyurl.com/mda2hp). The DOW Office of Finance is also available to provide an amortization schedule upon request.
| 7 | Project surplus or shortfall will be listed on line "m".
| 8 | If a shortfall exists, adjust lines "g" (additional cash required) or "j" (additional receivables / pledges required). Keep in mind that a change in pledge may increase the debt service expense as a result of additional borrowing. Alternatively, adjust original project costs if a change in project scope is required.
- Questions may be directed to the Diocese of Winona Office of Finance: 507-858-1248 -